## Sheet1
Project | TQ Num | Date added | Query/Subject | Date submitted | Submitted by | Submitted to | Answered by | Answered date | Resolved | Answer
ELEC5552 | 1 | 2021-08-01 | The simplification of FPGA development process | 2021-08-01 | Bo Wang | Ali Kharrazi | Ali Kharrazi | 2021-08-04 | Yes | Quaturs will deal with all the procedures of FPGA automatically, so it does not need any operation of human.
ELEC5552 | 2 | 2021-08-02 | The detailed requirements of iimproving lab manual | 2021-08-02 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-08-03 | Yes | there are no clear tasks or design operation, but the supervisor gives several points should be considered.
ELEC5552 | 3 | 2021-08-05 | The sample rate to determine nyquist frequency for FIR filters | 2021-08-05 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-08-05 | Yes | The sample rate should be the max sample rate available (limited by the board).
ELEC5552 | 4 | 2021-08-05 | lab manual limitations and requirements (time limit, expectations, ect) | 2021-08-05 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-08-05 | Yes | Students are required to complete lab activity in three hours, further lab activities can be completed in a lab report or other assessment outside of this time limit. Only the basic functionality is required to be included in the lab manual, students are required to interact with VHDL code (we do not want a 'blackbox' system of IP cores connected). The lab standard should not be difficult (students should average a high mark) and it is assumed F2F
ELEC5552 | 5 | 2021-08-05 | What saftey and risk assessments do we need to consider for the lab activty | 2021-08-05 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-08-05 | Yes | We are required to generate a saftey analysis, if required a lab introduction will need to be prepared (given the risk associated with lab procedures is high enough). The saftey analysis must consider hazards, probability and conseqeunces with a saftey management plan.
ELEC5552 | 6 | 2021-08-05 | Budget Considerations | 2021-08-05 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-08-05 | Yes | Our design should not be limited by budget, all cost from TQs (will recieve an invoice for all TQs answered) to faculty memeber costs (assume 50$ an hour) to utilities from the builidng (charged as a percentage of total budget for indirect cost) must be considered along with cost from hardware.
ELEC5552 | 7 | 2021-08-10 | Concept of constraint | 2021-08-10 | Thomas Overmeire | Gupreet Singh Gill | Gupreet Singh Gill | 2021-08-10 | Yes | The requirements are not unlimited, there are some elements limiting the scope of requirements, which are called constraints. The format of them in requirement analysis is up to the team. It could be one table containing all the constraints with the corresponding requirements; constraints could also be listed under each requirement.
ELEC5552 | 8 | 2021-08-10 | Techinical and general requirements in RA | 2021-08-10 | Thomas Overmeire | Gupreet Singh Gill | Gupreet Singh Gill | 2021-08-10 | Yes | The team need to confirm if there are only technical requirements or some general requirements are included by reviewting the guideline
ELEC5552 | 9 | 2021-08-15 | Could use java tool when coding? | 2021-08-12 | Info session | Ali Kharrazi | ALi Kharrazi | 2021-08-12 | Yes | It could be used during testing, but in the design it does need a ADC or other converters but not java codes.
ELEC5552 | 10 | 2021-08-15 | Flash memory | 2021-08-12 | Info session | Ali Kharrazi | ALi Kharrazi | 2021-08-12 | Yes | There is a flash memory in FPGA and we could upload the code on it. So you could ask FPGA to reprogram the code everytime the FPGA powers up.
ELEC5552 | 11 | 2021-08-15 | Could we use other simulation tool like the one in Quartus instead of Modelsim | 2021-08-12 | Info session | Ali Kharrazi | ALi Kharrazi | 2021-08-12 | Yes | No. In this unit, what professors desire to see is Modelsim simulation.
ELEC5552 | 12 | 2021-09-13 | Category of requirement | 2021-08-09 | Bo Wang | Ali Kharrazi | Ali Kharrazi | 2021-08-19 | Yes | Define the category first, then analyze the requirements. The criteria for categorization could be multiple.
ELEC5552 | 13 | 2021-09-13 | specific requirements of PDR & CDR | 2021-09-12 | Jonathan Louw | Ali Kharrazi | Ali Kharrazi | 2021-09-13 | Yes | Basically what happens in PDR and CDR is the same. You review your design to make sure your design meet requirements. The difference would be on what you are reviewing. In PDR, you have a preliminary high-level design and in CDR you have detailed design (component level).